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Notes

In progress

Enquire with local 

charity about defibs Ally 30/04/2026Medium 

Chasing for a response 

from previous 

correspondence

On going issue

Drains need to be 

cleared on main street 

as only some were done.

Councilor Gordon & 

Councilor Harris 30/04/2026Medium 

Request from Cllr 

Gordon to identify 

which drains are 

blocked. Simon 

responded with list on 

22/06/26 

In progress

New notice boards are 

in progress being made 

by Kevin Ally/Boyd 01/05/2026Medium  In progress

In progress

Organise meeting with 

council roads dept for 

the sub-group Boyd  30/04/2026Medium 

Await response from 

Moray Council 

following CEO visit

In progress

Apply for various bids 

and grants. Berry Burn, 

for polytunnel, funding Boyd 29/03/2026High Work ongoing

In progress

Posters for events and 

events on a calander for 

the year Emma 10/04/2026Medium 

Ongoing. Linda will 

pass detials for craft 

event so posters can 

be drafted. 

In progress

Pursue getting a floor 

cleaning machine Boyd/Linda 30/04/2026Medium 

Demo machine to be 

pursued

In progress

Contact Deborah Duke 

at Moray council to 

define village area Simon 10/04/2026Medium 

Contact made and 

Simon followed up. 

New name provided by 

Cllr Gordon who may 

be able to assist.  

In progress

Arrange metting with 

Thomas Hampson or 

Karen Grieves regarding 

Roads Boyd, Michael Last, Simon 30/06/2026Medium  15/04/2026

Pending response from 

Moray Council 

following CEO visit

In progress

Meet with Tom to 

discuss AVC website Emma & Simon 15/05/2026Medium  15/04/2026

Meeting held with 

Tom. Some 

reformatting made to 

website, which will 

continue to be refined. 

In progress

Speyside council 

meetings- find out why 

we arent able to 

participate. Speak to 

Deborah Duke? Simon 15/06/2026Medium  15/04/2026

Response passed to 

Boyd for his 

consideration. 

In progress

Explore funding available 

from HIE for 

development of new 

website Boyd 30/06/2026Medium  21/05/2026Being followed up. 

Completed

Develop action plan in 

preperation for AGM in 

September  Emma/Simon 30/07/2026Medium  21/05/2026

On agenda at meeting 

24/06/26. 

In progress

Seek a local interim 

solution for grass cutting 

of playpark and field  Boyd 30/06/2026High 24/06/2026

In progress

Commission a change of 

RHI meter in the hall, 

with a costing to be 

procured first.  Ally 15/07/2026High 24/06/2026


Archiestown Village Council

Reg. Scottish Charity Number:  SC001696


Archiestown Village Council Meeting
Wednesday 24th June 2026, Village Hall
7.30pm

Minute
1) Welcome
The Chair welcomed everyone to the meeting. Present: Boyd Ross (Chair); Michael Griffin; Linda Bracken; Emma Griffin; Sally Bruce; Ally Bruce; Simon Bokor-Ingram.
The Chair has received a resignation from Michael Last prior to this meeting, with immediate effect, which is due to him reducing his membership on committees. The Chair thanked Michael for all his input during his tenure. 
2) Apologies
Apologies received from Cllr Juli Harris; Cllr David Gordon; Cllr Derek Ross; Gillian Jones; Sean Jones; Anne Marshall.  
3) Letter of concern  
The meeting confirmed that the letter had been received and read, and that the nature of the concerns raised was understood. Having discussed the matter, the meeting noted that the facts as understood by the Village Council do not align with those set out in the letter. The Village Council remains clear on its constitution and its role as a voice for village concerns. Members also wished to emphasise that they are volunteers, doing their best to help make the village the best possible place to live. Local residents remain welcome to attend any Village Council meeting.
4) Approval of minute of meeting held on 21st May 2026
Proposed by Ally Bruce. Seconded by Michael Griffin. 
5) Action tracker updates
Updated as attached to this minute. Added action for change of RHI meter. 
6) Councillor’s business
Cllr Gordon chasing up the high street drainage issue, having asked for a list of blocked drains, which was emailed on the 22nd June. 
7) Group update on roads
A response is awaited regarding the unadopted roads issues following the CEO’s visit. The graduated speed limit for the village is due to be installed but has been delayed due to critical works elsewhere in Moray. The Village Council will continue to monitor the installation timeline to help ensure that the work is completed this year.
8) Group update on communication
Suggestion to put a thanks to folk who tend to village flowers in next newsletter. Newsletter to be published by end of July is being drafted. 
9) Group update on play park renewal
Work on new playpark underway. Estimated 5 week completion time. For future grass cutting the aim is to purchase machinery that is also adaptable to helping in winter weather. In the meantime Boyd will look to arrange a local solution pending our ability to purchase all season equipment- to be added to action tracker. 
10) Group update on fundraising and events
An event to mark the opening of the playpark will be arranged once the completion date is confirmed. The meeting agreed to begin provisional planning for an official opening event on 22nd August, while recognising that this date remains subject to confirmation. It was also agreed that the next newsletter should highlight the ongoing fundraising efforts, including planned purchases such as mowing equipment and hall blinds.
11) Treasurer Report 
£1,637.88 cash
£7,593.37 in bank

£9,231.25 total
Windfarm contingency available for draw down will be included in future reports. 

RHI require a change of meter for the hall in order that we continue to receive a rebate. Work commissioned to change the meter, with a costing to be the first part of that commission. 
12) Hall blinds proposal
Michael Griffin presented a range of hall blind options, taking account of quality, compatibility and cost. The meeting agreed to proceed with a proposal for manual blinds, supported by appropriate ladder apparatus to allow safe working at height. It was agreed that windfarm funding should be used for this purchase, at an estimated cost of approximately £2,000.
13)  Planning notifications
 None. 
14)  AGM 2026 and action plan 
The AGM 2026 and action plan were completed as attached. An additional action is to be added to ask one of the Councillors to chair the part of the meeting where Village Council office bearers are selected. The meeting agreed to confirm the provisional date of Wednesday 30th September.
15)  AOCB
· Tweed available on 22nd August, so potential for them to be part of official playpark opening, or as a follow on event that day. 
· Ovo have also specified that we install a smart meter for the hall. Meeting agreed that Ovo should be allowed to make the change (16th July.)
16)  Next meeting
Wednesday 22nd July, 7.30pm, village hall. 
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