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Notes

In progress

Enquire with local 

charity about defibs Ally 30/04/2026Medium 

Chasing for a response 

from previous 

correspondence

On going issue

Drains need to be 

cleared on main street 

as only some were done.

Councilor Gordon & 

Councilor Harris 30/04/2026Medium 

Request from Cllr 

Gordon to identify 

which drains are 

blocked. Simon 

responded with list on 

22/06/26 

In progress

New notice boards are 

in progress being made  Ally/Boyd 01/05/2026Medium 

In progress, with board 

being made for 

pavilion

In progress

Organise meeting with 

council roads dept for 

the sub-group Boyd  30/04/2026Medium 

Await response from 

Moray Council 

following CEO visit

In progress

Apply for various bids 

and grants. Berry Burn, 

for polytunnel, funding Boyd 29/03/2026High Work ongoing

In progress

Posters for events and 

events on a calander for 

the year Emma 10/04/2026Medium  Ongoing.

In progress

Pursue getting a floor 

cleaning machine Boyd/Linda 30/04/2026Medium 

Demo machine to be 

procured in August, 

and bid to be made to 

fund machine

In progress

Contact Deborah Duke 

at Moray council to 

define village area Simon 10/04/2026Medium 

Contact made and 

Simon followed up. 

New name provided by 

Cllr Gordon who may 

be able to assist.  

In progress

Arrange metting with 

Thomas Hampson or 

Karen Grieves regarding 

Roads Boyd, Michael Last, Simon 30/06/2026Medium  15/04/2026

Pending response from 

Moray Council 

following CEO visit

In progress

Commission a change of 

RHI meter in the hall, 

with a costing to be 

procured first.  Ally 15/07/2026High 24/06/2026Being chased up

In progress

Set a date for official 

opening ceremony for 

playpark  Emma/Ally 26/08/2026Medium  22/07/2026

Emma will liase with 

school. Ally to Liaise 

with Council CEO 

office. 

In progress

Set prices for the 2026 

new years eve Ceilidh  Boyd 30/09/2026Medium  22/07/2026

Ensure that over next 

two meeting cycles the 

event is priced and 

organised 


Archiestown Village Council

Reg. Scottish Charity Number:  SC001696


Archiestown Village Council Meeting
Wednesday 22nd July 2026, Village Hall
7.30pm

Minute
1) Welcome
The Chair welcomed everyone to the meeting. Present: Boyd Ross (Chair); Linda Bracken; Sean Jones; Emma Griffin; Michael Griffin; Sally Bruce; Ally Bruce; Simon Bokor-Ingram.
2) Apologies
Cllr Juli Harris; Cllr David Gordon; Cllr Derek Ross; Gillian Jones; Anne Marshall.
3) Approval of minute of meeting held on 24th June 2026
Approval proposed by Ally Bruce; seconded by Linda Bracken. 
4) Action tracker updates
Updated as per tracker attached to this minute. 
5) Councillor’s business
None.
6) Half year update on AVC Priorities 
Boyd presented the paper and highlighted opportunities for new initiatives, provided AVC continues to show that it can manage current assets well and handle risks effectively. The unadopted roads issue remains high risk and is still the most pressing issue for the village. The recommendations in the paper were agreed unanimously.
7) Group update on roads
Boyd to contact Council CEO to follow up post their visit to the village. 
8) Group update on communication
Viewings on AVC Facebook are growing significantly. Many more posts made in the last month which are generating more interest in the Facebook page. 
9) Play park official opening
A proposal was made to hold an official opening later this year. The local school could be invited to bring children to the play park for the ceremony, and children involved in the play park development could see the completed project. A film show at the hall could also be offered. Emma will liaise with the school. Ally will liaise with the Council to check when officials may be available to attend.
10) Group update on fundraising and events
Events are being planned for Halloween and Christmas, including the lights switch-on and a Christmas fair. The pub quiz night will be held on a different date from the lights switch-on. Michael will draft provisional dates. Ticket prices for the Ceilidh still need to be agreed.
11) Treasurer Report
Cash £505.38; bank £7560.09; total £8654.47. Windfarm balance to be reported on an ongoing basis to each meeting from the next update. 
12) Draft newsletter 
Agreed with minor adjustments to be made, with new dates to be added for events discussed at this meeting. 
13) Hall blinds update
It was agreed that windfarm monies will be drawn down to fund the hall blinds and associated equipment.
14)  Planning notifications
None. 
15)  AGM 2026 and action plan
The AGM 2026 action plan was agreed, with one change: potential new members will be invited through the newsletter to contact the AVC Secretary.
16)  Forestry and Land Scotland consultation
Noted. 
17)  AOCB
· Rubble has been tipped into the halls brown bin from an unknown source. Michael to try empty and take to recycle centre. 
18)  Next meeting
Wednesday 26th August, 7.30pm, village hall
Action tracker attached on next page.
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