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Notes

Completed AVC annual statement Boyd  15/05/2026Medium  Submitted to OSCR.

Completed

Chase rebate for pellet 

burner Ally 20/04/2026High

Final payment 

received.  

In progress

Enquire with local 

charity about defibs Ally 30/04/2026Medium  Being followed up

On going issue

Drains need to be 

cleared on main street 

as only some were done.

Councilor Gordon & 

Councilor Harris 30/04/2026Medium 

Continues to be raised 

with Cllrs at each 

meeting. Simon to 

email Cllrs Gordon and 

Harris- email sent 

25/05/2026 

In progress

New notice boards are 

in progress being made 

by Kevin Ally/Boyd 01/05/2026Medium  One board fixed

In progress

Organise meeting with 

council roads dept for 

the sub-group Boyd  30/04/2026Medium 

Await response from 

Moray Council 

following CEO visit

Completed

Edit and send newsletter 

to be printed. Emma 29/03/2026High Completed

In progress

Apply for various bids 

and grants. Berry Burn, 

for polytunnel, funding Boyd 29/03/2026High Work ongoing

In progress

Posters for events and 

events on a calander for 

the year Emma 10/04/2026Medium  Ongoing

Completed

Find out if there is cash 

in the windfarm pot Ally/Boyd 31/03/2026Medium 

circa £32k available 

for draw down 

In progress

Pursue getting a floor 

cleaning machine Boyd/Linda 30/04/2026Medium 

Demo machine to be 

pursued

In progress

Contact Deborah Duke 

at Moray council to 

define village area Simon 10/04/2026Medium 

Contact made and 

Simon to follow up 

Closed

Speak to school parent 

councill about 

volunteers to supervise 

school bus Emma 30/04/2026High 15/04/2026

Closed out and no 

further action

In progress

Arrange metting with 

Thomas Hampson or 

Karen Grieves regarding 

Roads Boyd, Michael Last, Simon 30/06/2026Medium  15/04/2026

Pending response from 

Moray Council 

following CEO visit

In progress

Meet with Tom to 

discuss AVC website Emma & Simon 15/05/2026Medium  15/04/2026Being followed up

Completed

Find out who owns the 

land behind houses on 

North Lane Boyd 30/05/2026Medium  15/04/2026

Boyd to pass 

information to Cllr 

Harris

In progress

Speyside council 

meetings- find out why 

we arent able to 

participate. Speak to 

Deborah Duke? Simon 15/06/2026Medium  15/04/2026Being followed up

In progress

Explore funding available 

from HIE for 

development of new 

website Boyd 30/06/2026Medium  21/05/2026

In progress

Develop action plan in 

preperation for AGM in 

September  Emma/Simon 30/07/2026Medium  21/05/2026


Archiestown Village Council

Reg. Scottish Charity Number:  SC001696


Archiestown Village Council Meeting
Thursday 21st May 2026, Village Hall
7pm

Minutes
1) Welcome
The Chair welcomed everyone to the meeting. Present: Boyd Ross (Chair); Ally Bruce; Sally Bruce; Michael Griffin; Michael Last; Simon Bokor-Ingram.
2) Apologies
Apologies were received from: Cllr Derek Ross; Emma Griffin; Anne Marshall; Cllr David Gordon; Gillian Jones; Sean Jones; Linda Bracken.
3) Approval of minute of meeting held on 15th April 2026
The minutes of the last meeting on 15th April 2026 were presented and agreed as written, with Michael Griffin proposing their adoption, and Michael Last seconding that motion. The minutes were agreed. 
4) Feedback on Moray Council CEO visit
A meeting was held at 5.30pm to 6.30pm with the Moray Council CEO, who had kindly agreed to visit the village and to hear about the endeavours of the village council. Those present walked from the village hall to the playpark, along North Lane, and then proceeded up South Lane and returned to the hall. Topics discussed included the plans for the new playpark, and the dubiety of whether some roads within the village are adopted or unadopted. It was agreed that we would work collaboratively between Moray Council and the village council, exploring the roads issue together to reach a position of mutual understanding. Present at this event were: CEO Karen Greaves; Cllr David Gordon; Boyd Ross; Ally Bruce; Sally Bruce; Michael Griffin; Michael Last; Simon Bokor-Ingram. 
5) Action tracker updates
The updated action tracker is attached to these minutes.  
6) Councillor’s business
Cllr David Gordon had joined the meeting with the Moray Council CEO visit, but could not attend the village council meeting. David had kindly picked up issues during the visit, including the ongoing highway drainage issues. Action: Simon Bokor-Ingram to email David and Cllr Juli Harris about the ongoing drainage issues, as remain unresolved. 
7) Group update on roads 
It was agreed that the next step was to wait for a response from Moray Council following the CEOs visit.
8) Group update on communication
Boyd shared that we can get funding from Highlands and Islands Enterprise to develop our village council website. Boyd to pursue this, and then hand over to the co-secretaries. Agreed that we need a new and revamped website, as communication has created challenges more recently. Linked discussion on the constitution, and the advantages of changing the governing arrangements. Action: Boyd to pursue website funding from HIE. 
9) Group update on play park renewal
Michael Griffin fed back on a 7th May meeting held on-site to plan out the spatial elements for the new playpark. The project is delayed as the contractors are running behind schedule and still working on the Aberlour playpark. Once we know a completion date for the Archiestown playpark we can plan an official opening, which would ideally take place before the schools return after the summer holidays. 
10)  Group update on fundraising and events
Agreed that Tweed to be booked for Hogmanay, with pricing to be same as last year, with more specificity as to age of children that receive free tickets. Whisky tasting night made circa £200 and was enjoyed by all. 
Suggestion for community tidy up day/s, both around and in the hall, and the wider village. 
11) Treasurer Report
£1637.88 cash, and £10073.05 in bank. This is a significantly improved position, largely due to the receipt of rebates for the heating system. In addition, there is £31900 available to draw down from windfarm funding, as and when we spend on specific items. 
12)  Planning notifications
The only notification in our locality was for the extension of an existing planning permission.  
13)  AGM 2026
Discussion centred on how we convey the essence of what our remit is as a village council prior to the AGM to help individuals decide if they want to be part of the committee, perhaps in a village newsletter to advertise the forthcoming AGM. Suggestion of an open meeting prior to the AGM for any potential committee members to self nominate, and find out more about the AVC. 
Will be a tight turnaround for Ally having the financial report ready for AGM, as our financial year ends at end of August. Suggestion to host a hybrid AGM so more folk could participate by being online. 
      Action: Co-secretaries to pick up these discussion points and set out a timetable in the run up 

      to the AGM to cover the actions needed. 
14)  AOCB
Pellets donated to hall need transporting from donor. Logistics being organised by Boyd. 
15)  Next meeting
Wednesday 24th June at 7.30pm, village hall. 
Action tracker: 
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